## Daily Activity
DATE | TASK | ACTIVITY | ACTION ITEM | PRIORITY | DUE DATE | STATUS
16/11/2021 | Investigate AWS latency and cost increase.
16/11/2021 | TIESERVER-11163: An .exe application does not get blocked/deleted even though the external reputation is set to 15 by ATP.
16/11/2021 | TIESERVER-11279: TIE Health check is failing in AU Partition.
16/11/2021 | TIE AWS Perl build script analysis.
16/11/2021 | Dev meet to decide on TIESERVER 11163
23/11/2021 | SCRUM ceremonies |  |  |  |  | COMPLETE
24/11/2021 | TIESERVER-11163: An .exe application does not get blocked/deleted even though the external reputation is set to 15 by ATP.
Reputation Change Event process
JIRA changes
25/11/2021 | Perl build scripts
TIE on Azure
TIESERVER-10182: subjectIdentity is duplicated.
Discussion with DXL team (Arvind) with Rishabh Nigam.
Investigate endpoint publishing to DXL topic.
Reach out to Arvind post Vadi call for MLOS dependency.
DXL topic configuration for AWS costing
Investigate DXL topic authorization.
26/11/2021
29/11/2021 | Analyze TIESERVER-11163: Reputation Change Event flow.
2021-12-01 | Meetings on TIESERVER-11163
Environment setup on VM
2021-12-02 | Nikhil discussion
Anomali - Reputation
AWS cost - Db temp tables/JOINS
11163 - Babloo
|  | VM environment | Steps noted.
TSET-9767
Call with MOVE team
2021-12-03 | TIESERVER-11389: Identify Reputation multiple rows.
2021-12-06 | TIESERVER-11389
2021-12-07 | TIESERVER-11389 | Identified
Marked Resolved
2022
TIESERVER-11477: TIE - Fire Eye Integration
2022-01-06 | TIE - ATD/ATP discussion with Fire Eye | Fire Eye moved on to ATD and ATP
| Discussion with Nick Wilson/Niel Clausen on JCM-4747 |  | No action item
2022-01-07 | TIESERVER-11477 - Fire Eye integration
TIE - IPE code base discussion with Jagadish
Analyse TIE - ATD file submission
Setup environment for file submission/log analysis.
2022-01-10 | Day off - POWER outage
409814 | Investigate TIESERVER-11460: TIE 3.0.1.154.1 On-Prem Server ISO deployment failure. | Created subtask TIESERVER-11599 for Narayan.
| Satya discussion on SDL blockers | Satya dropped mail to John Corkish+Harish.
| TIESERVER-11569: ATD file submision in TIE | Identified code points.
| Banco de Chile call on TIESERVER-11163 | Postponed to tomorrow.
2022-01-12 | Investigate TIESERVER-11460: TIE 3.0.1.154.1 On-Prem Server ISO deployment failure. | Resolved with Satya started new build.
| CVE-2021-42392 Detail | No H2 Dependancy found on Investigation in codebase.
| MLOS3 upgrade action. | Satya identified JIRA stories from previous team. Tasks mentioned (with story points) but need more analysis to go further.
2022-01-13 | Investigate TIESERVER-11460: TIE 3.0.1.154.1 On-Prem Server ISO deployment failure. | Build resulting in same errror taking up for detailed investigation.
MAINFEST changes to bootstrap.jar resolved issue.
| Harish SDL call. | metrics-elasticsearch-reporter-2.2.0.jar - version 2.2 jti_server_aggregator.jar Spring Framework5.3.13 H2 vulnerability (https://nvd.nist.gov/vuln/detail/CVE-2021-42392)
2022-01-14 | PUBLIC HOLIDAY
2022-01-17 | TIESERVER-11569: TIESERVER-11477 TIE - ATD file submission investigation. | Identified the flow for sample (file) submission. | Examine functional flow on test environment.
Created sequence diagram.
2022-01-20 | TIESERVER-11569: TIESERVER-11477 TIE - ATD file submission investigation. | Presentation preperation.
2022-01-22 | TIESERVER-11569: TIESERVER-11477 TIE - ATD file submission investigation. | Presentation delivered to Natesh.
2022-01-24 | TIESERVER-11629: [Dev] Get dependent product compatible MLOS3 version. | Interacted with MAR - Anil Govada (QA Mgr). Redirected to Sean Twomey (Dev Mgr).
Updated TIESERVER-11629
| TIESERVER-11477: FireEye DOD/MVX - TIE Integration: Initial analysis & TIESERVER-11569: TIESERVER-11477 TIE - ATD file submission investigation. | Presentation material approved by Rajeev Joshi (ATD).
Discussion with Jayesh Singh (QA Lead)
|  | Presentation sent to Art for feedback. | Incorporate Art feedback.
2022-01-25 | Discussed with Rajat Saxena + Ankit Jain TIE-Insights integration. | Identified the action items. | Investigate TIESERVER current functionality.
| Looking into test case failures with Babloo. | Could be due to changes on dxl codebase and dxlclient jar.
2022-01-26 | PUBLIC HOLIDAY
2022-01-27
2022-01-31 | Insights exploration as discussed with Rajat Saxena (Ar. Architect).
2022-03-04 | TIESERVER-11794: IAM / DXL databus | One Note added. | Reach Kshitiz + Arun on GSD vis-à-vis IAM per Partition
IAM videos.
On call with Sajeed - Debug TIE DXL connectivity issue.
| Goal setting | Created worksheet

## Sheet2
Pending
In progress
On Hold
Blocked
Complete